## Project profile
Defect Reporting
Project ID | PRJ_Democart_browsing and cart _001
Project Name | Democart_browsing and cart
Prepared/Modified by | Role | Date of Preparation
Divyangna Gupta Abir Coomar Subhasish Bhattacharjee Akshay Dhongadi Akshay Gupta Praveen | Test Engineer | 28th February,2018
Reviewed by | Role | Date of Review
Test Lead
Approved by | Role | Date of Approval
Test Manager
Circulation List
Version Number | 1

## defect report
Project ID: PRJ_Democart_browsing and cart _001 |  | Project Name : Democart_browsing and cart
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Fixed By | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments
DF_Democart_01 | Shopping Cart | The update button is found to be accepting Invalid values for quantity field. | Detailed Description: The update button is found to be accepting Zero,Negative and blank values for quantity field.It is not showing any error message. Steps To reproduce the bug: 1. Open Browser 2. The Home Page should be displayed. 3. Click on ''Shopping Cart" link , it navigates to Shopping Cart page. 4.Give Invalid input as quantity 5. On clicking the Update button the product get updated with the quantity accordingly. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the update button is not displayed error message as axpected . | Coding | google chrome | Internal Dev | Low | Medium | 1.1 | Build 1.0 | 2018-02-28 | Subhasish Bhattacharjee |  | ACT | Test Cycle 1 | TC_ShoppingCart_04
DF_Democart_02 | Shopping Cart | The "Get Quotes" button is found to be accepting Invalid post code. | Detailed Description: The "Get Quotes" button is found to be accepting Invalid post code.. It is not showing any error message. Steps To reproduce the bug: 1. Open Browser 2. The Home Page should be displayed. 3. Click on ''Shopping Cart" link ,it navigates to Shopping Cart page. 4.Give invalid post code under Estimate Shipping & Taxes 5. Click on Get Quotes button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the Get Quotes button is not displayed error message for Invalid post code as axpected . | Coding | google chrome | Internal Dev | Low | Medium | 1.1 | Build 1.0 | 2018-02-28 | Subhasish Bhattacharjee |  | ACT | Test Cycle 1 | TC_ShoppingCart_16 | [7 empty] | Is it ok to accept all kind of data as user name ?
DF_Democart_03 | HTC Touch HD product page | The "Add to cart" button is found to be accepting Invalid quantity in the quantity field. | Detailed Description: The "Add to cart" button is found to be accepting Invalid quantity in the quantity field. It is not showing any error message. Steps To reproduce the bug: 1. Open Browser 2. The Home Page should be displayed. 3. Go to HTC Touch HD product Screen 4.Leave Quantity field blank and click "Add to cart" button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the "Add to cart" button button is not displayed error message for blank field as axpected . | Coding | google chrome | Internal Dev | Low | Medium | 1.1 | Build 1.0 | 2018-02-28 | Subhasish Bhattacharjee |  | ACT | Test Cycle 1 | TC_HTC_Touch_ID_08
Note on A3: Alphy Chenganiyadan Give a unique number for the Defect Id
Note on B3: Alphy Chenganiyadan: Give the name of the module being tested
Note on C3: Alphy Chenganiyadan: Summarize the defect in 1 or 2 lines
Note on D3: Alphy Chenganiyadan: A detailed description of the defect
Note on E3: Alphy Chenganiyadan: Categorize the defect into the one of the values given in the drop down list
Note on F3: Alphy Chenganiyadan: Mention the name of the browser the defect was found in.
Note on G3: Alphy Chenganiyadan: Mention the environment in which the defect was found.
Note on H3: P0 defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption P1 defect is a defect wherein a function does not work and a tedious work around exists. e.g. One of menu options does not work. P2 defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. P3 defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling. “High” severity defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption, some of the menu functions do not work “Medium” severity defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. “Low” severity defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling.
Note on I3: Prioritize the defect
Note on J3: Alphy Chenganiyadan: Enter the Release # in which the defect was detected.
Note on K3: Alphy Chenganiyadan: Enter the Build # in which the defect was detected.
Note on L3: Alphy Chenganiyadan: Mention the date the defect was reported
Note on M3: Alphy Chenganiyadan: Name of the person who reported the defect.
Note on N3: Alphy Chenganiyadan: Name of the person the defect is assigned to.
Note on O3: Alphy Chenganiyadan: Can have values: VERIFIED CLOSED FIXED ACT-Active CNR-Could Not be Reproduced NOD- Reported Bug Not a Defect REP- Repeated
Note on P3: Alphy Chenganiyadan: Values can be: PPR-Peer to Peer Review PR-Peer Review SR-Self/Programmer Review QPR-10% Quality Probe(Review) RT-Random Testing UTC-Using Test Cases
Note on Q3: Alphy Chenganiyadan: Mention the Test Case No that the defect was found while testing
Note on R3: Alphy Chenganiyadan: Name of the person who fixed the defect.
Note on S3: Alphy Chenganiyadan: Mention the date the defect was Fixed
Note on T3: Alphy Chenganiyadan: Mention the date the defect was verified
Note on U3: Alphy Chenganiyadan: Name of the person who will be verifying whether the defect has got fixed after the defect has being worked upon
Note on V3: Alphy Chenganiyadan: Enter the Release # in which the defect was available for verification
Note on W3: Alphy Chenganiyadan: Enter the Build # in which the defect was available for verification
Note on X3: Alphy Chenganiyadan: Attach the proofs showing the defect-screenshots,temp files,etc
Note on Y3: Alphy Chenganiyadan: Should include all the comments on the defects till date by all touching the defect.It should be captured date wise.